## RBC CRM to S4
Sl.No | Execution Steps.. | Objective | Owner | System | Comments
1 | Build Sandbox System | Set up sandbox with business functions activated | RBC | Sandbox
2 | Identify the custom code | Decision on the list of custom objects to be migrated to S/4 | RBC + SAP | Sandbox | SAP and RBC to collaborate on this
3 | Import of the custom code and configurations | Import the custom code and configuration into the target environment | SAP | Sandbox
4 | Functional Validation | Sanity check(Functional Check) | RBC + SAP | Sandbox
5 | Functional Adjustments | Any functional adjustments needed post imports | SAP | Sandbox
6 | KUT conversion | Extension conversion to KUT(where ever possible) | SAP | Sandbox
7 | Code Remediation(Enhancements) | Update existing code to ensure compatibility with the target system | SAP | Sandbox
8 | Data Migration build | Migration of CRM transactions and Business Partner data | SAP | Sandbox
9 | SD Pricing set up |  | SAP | Sandbox
10 | Code Remediation(Interfaces) | Update existing code to ensure compatibility with the target system | SAP | Sandbox
11 | UI Adjustments | Changes required in the BSP components, navigation bar profile Logical link adjustements | SAP | Sandbox
12 | Functional testing | Functional Unit Testing(No end to end testing) | RBC + SAP | Sandbox
13 | Signoff |  | RBC | Sandbox
14 | Development system build |  | RBC | Dev
15 | Import of TR's from Sandbox to Dev |  | RBC | Dev
16 | Functional Testing | Sanity check(Functional Check) | RBC + SAP | Dev
16 | Data Migration test load |  | SAP | Dev
17 | Signoff |  | RBC | Dev
18 | Quality system build |  | RBC | QA
19 | Import of TR's from Dev to QA |  | RBC | QA
20 | Functional Testing | Sanity check(Functional Check) | RBC + SAP | QA
21 | Data load |  | SAP | QA
22 | SIT(SIT1 +…) |  | RBC | QA
23 | Signoff |  | RBC | QA
24 | Pre-prod system build |  | RBC | Pre Prod
25 | Import of TR's from QA to Pre-prod |  | RBC | Pre Prod
26 | Data load |  | SAP | Pre Prod
27 | UAT |  | RBC | Pre Prod
28 | Signoff |  | RBC | Pre Prod
24 | Prod system build |  | RBC | Prod
25 | Import of TR's from Pre-prod to Prod |  | RBC | Prod
29 | Cut over activities(Data load + TR imports +..) |  | RBC + SAP | Prod
30 | Go-Live |  | SAP | Prod
31 | Post Go-Live Support |  | SAP | Prod
This activities is prepared based in the assumption of Sandbox + Dev + QA + Pre Prod + Prod system landscape.
STMS transport path is available between the systems